TRIAL MANAGEMENT PLAN

IMM-2026-001

Version 1.0 — DRAFT

# Document Control

| Document Name | Trial Management Plan |
| --- | --- |
| Document ID | DOC-0002 |
| Artifact ID | 01.01.02 |
| Study ID | IMM-2026-001 |
| Sponsor | Fictional Pharma Ltd. |
| Therapeutic Area | Immunology / Allergy |
| Indication | Moderate-to-Severe Atopic Dermatitis |
| Study Phase | Phase II |
| Study Design | Randomized, Double-Blind, Placebo-Controlled |
| Investigational Product | IMM-101 |
| Level | Trial |
| Country | Global |
| Site | N/A |
| Version | 1.0 |
| Status | Draft |
| Document Date | 27-Jul-2026 |
| Owner | Clinical Operations |

# 1. Purpose

This Trial Management Plan (TMP) describes the operational framework for planning, conducting, overseeing, and closing the fictional IMM-2026-001 clinical trial. It defines key responsibilities, communication pathways, milestones, oversight activities, and escalation principles.

# 2. Study Overview

IMM-2026-001 is a fictional Phase II interventional study evaluating IMM-101 in adults with moderate-to-severe atopic dermatitis. The study uses a randomized, double-blind, placebo-controlled design and is planned for Türkiye, Germany, and Spain.

# 3. Study Governance

Clinical Operations will provide overall operational coordination. The Clinical Trial Manager will coordinate trial activities and maintain oversight of milestones, risks, vendors, and cross-functional communication. Functional leads remain accountable for activities within their areas.

# 4. Roles and Responsibilities

Key functions include Clinical Operations, Clinical Trial Management, Clinical Research Associates, Regulatory Affairs, Pharmacovigilance/Safety, Data Management, Biostatistics, Medical Monitoring, Quality Assurance, and Document Management.

# 5. Trial Milestones

Major milestones include study start-up, country and site feasibility, regulatory and ethics submissions, site activation, first patient first visit, recruitment, last patient last visit, database lock, study close-out, and TMF reconciliation.

# 6. Site Management

Site activities include feasibility, qualification, selection, initiation, routine monitoring, issue escalation, and close-out. Site-level documentation will be collected and filed to applicable TMF artifacts.

# 7. Communication Plan

Routine communication will use scheduled study team meetings, action trackers, email communication, and documented decision records where appropriate. Critical issues will be escalated to the responsible study lead.

# 8. Risk and Issue Management

Operational risks and issues will be identified, assessed, documented, assigned to owners, and tracked to resolution. Significant risks may require escalation, mitigation, or preventive actions.

# 9. Vendor and Third-Party Oversight

Where third parties support study activities, responsibilities, deliverables, timelines, and oversight expectations will be documented. Vendor performance and relevant records will be monitored.

# 10. Monitoring Oversight

Monitoring activities will follow the applicable monitoring strategy and plan. Monitoring findings, follow-up actions, and significant issues will be documented and escalated according to study procedures.

# 11. Safety Oversight

Safety information will be managed through the study's pharmacovigilance and medical safety processes. Safety-related records will be maintained in applicable TMF locations.

# 12. Data Management and Statistics

Data Management and Biostatistics will manage data-related activities, data quality, statistical planning, and analysis according to the study protocol and applicable plans.

# 13. Quality Management

The study will use quality and risk-based oversight principles. Deviations, significant findings, corrective actions, and preventive actions will be managed through applicable quality processes.

# 14. TMF Management

Trial records will be filed to the appropriate TMF artifact with required metadata. Clinical Operations and Document Management will support completeness, quality, timeliness, and inspection readiness.

# 15. Change Control

Material changes affecting study operations, timelines, responsibilities, or risk controls will be documented and assessed. Approved changes will be communicated to affected functions and reflected in relevant controlled documents.

# 16. Study Close-Out

At study close-out, outstanding activities and documents will be reconciled, site close-out will be completed as applicable, and TMF completeness will be assessed before archival.

# Revision History

| Version | Date | Owner | Description |
| --- | --- | --- | --- |
| 1.0 | 27-Jul-2026 | Clinical Operations | Initial draft for mock eTMF training project. |

TRAINING USE ONLY — This document is fictional and is not a record from a real clinical trial.